## Sprint 4 QA Alert We reviewe
ID | Category | Feedback Item | Priority | Status | Action Plan / Resolution
1 | Backend | POST /api/generate-certificate is missing; currently handled on frontend. | Critical | New | Move PDF logic to backend to meet Sprint 4 spec.
2 | Logic | Bias detection uses incorrect thresholds (>15pp/>8pp). | Critical | New | Align logic to exact spec: Hidden at <= 10pp, Visible at > 10pp.
3 | Content | Step 6 sense-check uses keywords instead of 20-domain mapping. | High | New | Map explicit domain-specific text across all 20 required domains.
4 | UI/UX | Step 7 training representation warning is static, not threshold-driven. | High | New | Refactor warning to trigger dynamically based on data thresholds.
5 | UI/UX | EU AI Act checklist lacks visible completion progress. | Med | New | Implement a progress bar or counter for checklist toggles.
6 | Branding | Failure case study colors (Blue) and Page Title (ML Tool) are incorrect. | Med | New | Update colors to Red/Amber/Green and rename title to HealthML.
7 | Testing | Playwright environment is broken (missing binaries/test package). | Critical | New | Install @playwright/test and required browser binaries.
8 | Testing | Test suite is insufficient (4 tests; 2 failing) for Sprint 4 criteria. | Critical | New | Develop comprehensive acceptance tests for Steps 1–7 E2E flow.